## BE - Tasks
SN | Task ID | Task | Module | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
1 | 101 | Develop backend API for adding new company | Company Management Workflow | [6 empty] | Backend API for storing and validating company details | Fields: Name, Address, Industry, Contact Info, Metadata. Validate mandatory fields.
2 | 102 | Create frontend form for company details input | Company Management Workflow | [6 empty] | Frontend form to input company details | Input fields with placeholders, tooltips, and validation rules.
3 | 103 | Validate company details on form | Company Management Workflow | [6 empty] | Validation system for form fields | Rules: Required fields, Email/Phone patterns, Unique name via API check.
4 | 104 | Implement Save functionality | Company Management Workflow | [6 empty] | Save button triggering API call with success/error feedback | Includes activity logging for changes.
5 | 105 | Add role-based permission management | Company Management Workflow | [6 empty] | Backend logic for roles and permissions | Roles: Manager, Assessor, Field Agent, Compliance Staff. Role hierarchy and access levels.
6 | 106 | Create frontend for role assignment | Company Management Workflow | [6 empty] | Interface for assigning roles and permissions | Dropdown for roles. Multi-select or drag-and-drop for permissions assignment.
7 | 107 | Send email invitations to team members | Company Management Workflow | [6 empty] | Email system to send setup links | Includes team member's role, permissions, and setup instructions.
8 | 108 | Enable association of team members with tasks | Company Management Workflow | [6 empty] | Functionality to associate team members with assessments/tasks | Links team members to specific assessments and roles.
9 | 109 | Update company information backend functionality | Company Management Workflow | [6 empty] | API for editing and saving updated company details | Tracks version history and logs all changes.
10 | 110 | Create frontend for editing company information | Company Management Workflow | [6 empty] | Editable company details form | Displays change logs in a sidebar or separate section.
11 | 111 | Enable report generation for assessments | Company Management Workflow | [6 empty] | Generate reports with company and assessment data | Fields: Name, Date, Assessor, Findings, Recommendations.
12 | 112 | Add staff management module to backend | Company Management Workflow | [6 empty] | Backend module for staff CRUD operations | Fields: Name, Role, Contact Info, Tasks, Associated Company.
13 | 113 | Create staff management frontend | Company Management Workflow | [6 empty] | Frontend interface for managing staff | Includes search, filter, and add/edit forms.
14 | 114 | Implement archive/delete functionality | Company Management Workflow | [6 empty] | Backend logic for archiving or deleting companies | Logs actions and maintains audit trail for transparency.
15 | 115 | Create confirmation prompts for archive/delete | Company Management Workflow | [6 empty] | Confirmation modal with warnings | Example: "Archived companies cannot be modified."
16 | 116 | Develop backend API for adding new clients | Client Management Workflow | [6 empty] | Backend API for storing client profiles | Fields: Name, Address, Contact Info, Assigned Company. Validate mandatory fields.
17 | 117 | Create frontend form for client details input | Client Management Workflow | [6 empty] | Frontend form to input client details | Input fields with placeholders, tooltips, and validation rules.
18 | 118 | Validate client details on form | Client Management Workflow | [6 empty] | Validation system for form fields | Rules: Required fields, Email/Phone patterns, Company association validation.
19 | 119 | Implement Save functionality for clients | Client Management Workflow | [6 empty] | Save button triggering API call with success/error feedback | Includes activity logging for changes.
20 | 120 | Implement client association with companies | Client Management Workflow | [6 empty] | Backend logic for linking clients to companies | Ensures that each client is tied to a valid company profile.
21 | 121 | Create frontend for client-company linkage | Client Management Workflow | [6 empty] | Interface for selecting and linking clients with companies | Dropdown for available companies. Display company name with client profile.
22 | 122 | Implement search functionality for clients | Client Management Workflow | [6 empty] | Backend API for searching clients based on criteria | Criteria: Name, Company, Contact Info.
23 | 123 | Create frontend for client search | Client Management Workflow | [6 empty] | Search bar with filters for name, company, or contact info | Includes pagination and sorting.
24 | 124 | Implement client profile update functionality | Client Management Workflow | [6 empty] | Backend API for updating client details | Editable fields: Name, Address, Contact Info, Assigned Company.
25 | 125 | Create frontend for editing client profiles | Client Management Workflow | [6 empty] | Editable form for client details | Displays change logs in a sidebar or separate section.
26 | 126 | Implement client profile deletion/archive | Client Management Workflow | [6 empty] | Backend logic for archiving or deleting client profiles | Logs actions and maintains audit trail for transparency.
27 | 127 | Create confirmation prompts for deletion | Client Management Workflow | [6 empty] | Confirmation modal with warnings | Example: "Archived client profiles cannot be modified."
28 | 128 | Develop backend API for calendar access | Calendar Scheduling Workflow | [6 empty] | API for retrieving tasks, assessments, and schedules | Filters: Company, Client, Assessment Type.
29 | 129 | Create frontend for calendar view | Calendar Scheduling Workflow | [6 empty] | Calendar UI showing upcoming tasks, assessments, and schedules | Include filtering options by company, client, or assessment type.
30 | 130 | Implement task/assessment scheduling feature | Calendar Scheduling Workflow | [6 empty] | Backend functionality to add new tasks or assessments | Fields: Date, Assigned Personnel, Location, Instructions.
31 | 131 | Create frontend for scheduling tasks/assessments | Calendar Scheduling Workflow | [6 empty] | Scheduling form with input fields for task details | Include date picker, personnel selection, and instruction fields.
32 | 132 | Set up notification and reminder triggers | Calendar Scheduling Workflow | [6 empty] | Automated notifications and reminders | Triggers: Task creation, updates, or upcoming deadlines.
33 | 133 | Create frontend for notification settings | Calendar Scheduling Workflow | [6 empty] | UI for configuring notification preferences | Options for email, in-app, or push notifications.
34 | 134 | Display scheduled events on user dashboards | Calendar Scheduling Workflow | [6 empty] | Dashboard view showing all scheduled tasks/events | Include user-specific filters and visibility controls.
35 | 135 | Develop integration with external calendar tools | Calendar Scheduling Workflow | [6 empty] | Sync functionality with Google Calendar or other external tools | Two-way synchronization for real-time updates.
36 | 136 | Create frontend for calendar integration settings | Calendar Scheduling Workflow | [6 empty] | UI for connecting external calendars | Options to enable/disable sync and manage tool connections.
37 | 137 | Implement approval workflow for new events | Calendar Scheduling Workflow | [6 empty] | Workflow to approve and finalize scheduled tasks | Includes notifications to involved parties upon approval.
38 | 138 | Create frontend for event approval process | Calendar Scheduling Workflow | [6 empty] | Approval interface for admins/managers | Include status indicators for pending/approved tasks.
39 | 139 | Test calendar synchronization and notifications | Calendar Scheduling Workflow | [6 empty] | Tested calendar synchronization and notification workflows | Ensure real-time updates, accurate notifications, and error handling.
40 | 140 | Validate calendar performance under load | Calendar Scheduling Workflow | [6 empty] | Performance-tested calendar module | Stress-test with a high volume of events/tasks to ensure scalability.
41 | 141 | Develop backend API for templates management | Assessment Templates Creation Workflow | [6 empty] | Backend API for creating, saving, and managing templates | Supports fields: Name, Type, Instructions, Scoring Mechanisms, Guidelines.
42 | 142 | Create frontend for templates section navigation | Assessment Templates Creation Workflow | [6 empty] | UI for accessing and navigating the "Assessment Templates" section | Includes a "Create New Template" button.
43 | 143 | Implement template creation functionality | Assessment Templates Creation Workflow | [6 empty] | Functionality for adding template fields and saving them | Fields: Text inputs, Checkboxes, Dropdowns, Pictures, Pre-built templates.
44 | 144 | Create frontend for template customization | Assessment Templates Creation Workflow | [6 empty] | Customization form for adding template fields | Includes preview mode to see the template structure before saving.
45 | 145 | Implement template publishing functionality | Assessment Templates Creation Workflow | [6 empty] | Backend API for publishing templates for company/client-specific use | Assign templates to companies, clients, or projects.
46 | 146 | Create frontend for publishing templates | Assessment Templates Creation Workflow | [6 empty] | UI to assign templates to companies, clients, or projects | Includes filter options for selecting specific entities.
47 | 147 | Implement mobile accessibility for templates | Assessment Templates Creation Workflow | [6 empty] | API for making templates available in mobile applications | Templates synced with field assessor tools.
48 | 148 | Develop mobile templates module | Assessment Templates Creation Workflow | [6 empty] | Mobile module for accessing and filling templates | Includes offline mode for template access and usage.
49 | 149 | Implement template management (update/archive) | Assessment Templates Creation Workflow | [6 empty] | Backend logic for editing, updating, and archiving templates | Archive outdated templates while retaining historical integrity.
50 | 150 | Create frontend for template management | Assessment Templates Creation Workflow | [6 empty] | UI for editing and archiving templates | Includes version control and logs for template updates.
51 | 151 | Test template creation and customization flows | Assessment Templates Creation Workflow | [6 empty] | Fully tested workflows for creating and customizing templates | Ensure templates work for various field types and guidelines.
52 | 152 | Test template publishing and assignment | Assessment Templates Creation Workflow | [6 empty] | Fully tested workflows for template publishing | Verify templates are properly assigned and accessible by intended users.
53 | 153 | Validate mobile access and syncing of templates | Assessment Templates Creation Workflow | [6 empty] | Ensure mobile syncing and offline mode functionality | Check template usability in low-connectivity scenarios.
54 | 154 | Performance testing for template management | Assessment Templates Creation Workflow | [6 empty] | Templates module tested for performance under heavy usage | Ensure scalability with large numbers of templates and users.
55 | 155 | Develop backend API for report generation | Generate Report Workflow | [6 empty] | API to retrieve completed assessments and generate reports | Fields: Assessment ID, Date, Risk Analysis, Recommendations, Compliance Status.
56 | 156 | Create frontend for report selection | Generate Report Workflow | [6 empty] | UI for selecting completed assessments for reporting | Filters by date range, assessment type, and other criteria.
57 | 157 | Implement report customization functionality | Generate Report Workflow | [6 empty] | Backend logic for customizing report content | Features: Format selection (PDF), adding graphs, images, and annotations.
58 | 158 | Create frontend for report customization | Generate Report Workflow | [6 empty] | UI for selecting sections and customizing report layout | Drag-and-drop interface for adding/removing report sections.
59 | 159 | Implement preview functionality for reports | Generate Report Workflow | [6 empty] | API to generate report previews | Temporary draft report for review and edits.
60 | 160 | Create frontend for report preview | Generate Report Workflow | [6 empty] | Preview window for reviewing report layout and content | Include options to add final comments or summaries.
61 | 161 | Implement report distribution options | Generate Report Workflow | [6 empty] | Backend logic for downloading, emailing, and storing reports | Permissions to control view/edit access for stakeholders.
62 | 162 | Create frontend for report distribution | Generate Report Workflow | [6 empty] | UI for selecting distribution methods (download, email, store) | Include status indicators for successful/failed deliveries.
63 | 163 | Set up email template for report sharing | Generate Report Workflow | [6 empty] | Email template with report link and summary | Supports adding recipient details and customizing email content.
64 | 164 | Implement report permissions and access control | Generate Report Workflow | [6 empty] | Logic for setting permissions and managing access control | Roles: Viewer, Editor. Ensure data security and privacy.
65 | 165 | Create frontend for report permissions | Generate Report Workflow | [6 empty] | UI for assigning view/edit permissions to specific users | Includes permission summary and modification history.
66 | 166 | Test report generation and customization workflows | Generate Report Workflow | [6 empty] | Fully tested workflows for generating and customizing reports | Verify accuracy of data and proper rendering of graphs/images.
67 | 167 | Test report distribution functionality | Generate Report Workflow | [6 empty] | Fully tested workflows for report sharing and permissions | Ensure email delivery, storage, and download options function as expected.
68 | 168 | Performance testing for report module | Generate Report Workflow | [6 empty] | Performance-tested report generation under high load | Test with a large number of assessments to ensure system scalability.
69 | 169 | Develop backend API for adding new users | User Management Workflow | [6 empty] | API for creating user profiles and linking them to company/client profiles | Fields: Name, Email, Role, Assigned Company/Client, Access Level.
70 | 170 | Create frontend for adding new users | User Management Workflow | [6 empty] | UI for entering user details and assigning to company/client | Includes role dropdown and access level options.
71 | 171 | Implement role-based permissions system | User Management Workflow | [6 empty] | Backend logic for managing roles and permissions | Roles: Admin, Assessor, Manager. Permissions: View, Edit, Delete, Create.
72 | 172 | Create frontend for assigning roles and permissions | User Management Workflow | [6 empty] | Interface for assigning roles and permissions | Includes summary of assigned permissions.
73 | 173 | Implement user invitation and setup system | User Management Workflow | [6 empty] | Backend logic for generating and sending account setup invitations | Email includes setup link, assigned role, and instructions.
74 | 174 | Create frontend for user invitation management | User Management Workflow | [6 empty] | UI to track and resend user invitations | Displays status of pending and completed setups.
75 | 175 | Implement login and role-based access control | User Management Workflow | [6 empty] | Access control system to restrict user actions based on assigned roles | Ensure compliance with assigned permissions.
76 | 176 | Create frontend for active user management | User Management Workflow | [6 empty] | UI for viewing and managing active users | Features: Update permissions, reset passwords, deactivate accounts.
77 | 177 | Develop activity logging system for user actions | User Management Workflow | [6 empty] | Logs of user actions for compliance and security purposes | Tracks changes, login activity, and permission updates.
78 | 178 | Create frontend for viewing activity logs | User Management Workflow | [6 empty] | UI for admins to view and search activity logs | Includes filters for date, user, and action type.
79 | 179 | Test user creation and role assignment workflows | User Management Workflow | [6 empty] | Fully tested workflows for adding users and assigning roles | Verify proper linking with company/client profiles and role-based access control.
80 | 180 | Test invitation and setup processes | User Management Workflow | [6 empty] | Fully tested workflows for sending and completing user invitations | Ensure setup link delivery and proper user account activation.
81 | 181 | Test active user management functionalities | User Management Workflow | [6 empty] | Fully tested management features for updating permissions and deactivating users | Verify compliance with security requirements.
82 | 182 | Validate activity logging and search accuracy | User Management Workflow | [6 empty] | Logs tested for accuracy and completeness under various scenarios | Ensure logs include all relevant user actions.
83 | 183 | Performance testing for user management module | User Management Workflow | [6 empty] | Performance-tested user management module under high load | Ensure system can handle a large number of users and actions efficiently.
84 | 184 | Develop backend API for subscription plans | Subscription Workflow | [6 empty] | API for retrieving and managing subscription plans | Plans: Pay as you go, Monthly, Annual, Enterprise. Includes features, limits, and pricing.
85 | 185 | Create frontend for subscription selection | Subscription Workflow | [6 empty] | UI for viewing and selecting subscription plans | Includes detailed plan descriptions and feature comparisons.
86 | 186 | Implement payment integration with Stripe | Subscription Workflow | [6 empty] | Payment gateway integration for processing subscription payments | Supports multiple methods: Credit Card, PayPal, etc.
87 | 187 | Create frontend for payment processing | Subscription Workflow | [6 empty] | Payment form for entering billing details and selecting payment method | Includes input validation and error handling for failed payments.
88 | 188 | Develop subscription activation logic | Subscription Workflow | [6 empty] | Backend logic for activating subscription plans upon successful payment | Adjusts user limits and access to modules as per the selected plan.
89 | 189 | Create frontend for subscription confirmation | Subscription Workflow | [6 empty] | Confirmation page and email notification for activated subscription | Includes details of the plan, start date, and renewal information.
90 | 190 | Implement subscription management features | Subscription Workflow | [6 empty] | Backend logic for upgrading/downgrading plans and updating billing details | Includes prorated charges for plan changes.
91 | 191 | Create frontend for subscription management | Subscription Workflow | [6 empty] | UI for viewing subscription status and managing plans | Includes upgrade/downgrade options, billing history, and notifications.
92 | 192 | Implement automated renewal reminders | Subscription Workflow | [6 empty] | System to send automated reminders for subscription renewal | Configurable reminder frequency (e.g., 7 days, 1 day before renewal).
93 | 193 | Create frontend for renewal notifications | Subscription Workflow | [6 empty] | UI for displaying renewal reminders in the dashboard | Includes links to renew or change subscription plans.
94 | 194 | Test subscription plan selection and activation workflows | Subscription Workflow | [6 empty] | Fully tested workflows for selecting and activating subscriptions | Verify accuracy of feature limits and access settings for different plans.
95 | 195 | Test payment integration and error handling | Subscription Workflow | [6 empty] | Fully tested payment workflows and error scenarios | Ensure secure handling of payment data and proper error messages for failures.
96 | 196 | Test subscription management functionality | Subscription Workflow | [6 empty] | Fully tested features for managing subscriptions | Verify smooth plan changes, billing updates, and renewal processes.
97 | 197 | Performance testing for subscription module | Subscription Workflow | [6 empty] | Performance-tested subscription workflows under high load | Ensure scalability for a large number of users and concurrent payments.
98 | 198 | Develop backend logic for trigger events | Notification and Reminder Workflow | [6 empty] | Logic to detect trigger events and initiate notifications | Events: New assessment, task deadlines, subscription renewals, user actions.
99 | 199 | Implement notification creation module | Notification and Reminder Workflow | [6 empty] | Module to generate notifications with relevant details | Fields: Event type, Date, User, Description, Action Link.
100 | 200 | Create frontend for managing notification triggers | Notification and Reminder Workflow | [6 empty] | UI for setting up and managing notification triggers | Admin interface for configuring triggers for specific events.
101 | 201 | Implement notification delivery system | Notification and Reminder Workflow | [6 empty] | Backend logic to send notifications via email, in-app, and push notifications | Includes integration with email and mobile push services.
102 | 202 | Create frontend for notification display | Notification and Reminder Workflow | [6 empty] | UI for displaying in-app notifications on the user dashboard | Includes unread/read status and action links.
103 | 203 | Implement user acknowledgment functionality | Notification and Reminder Workflow | [6 empty] | Backend logic to mark notifications as "read" or "completed" | Tracks acknowledgment status for each notification.
104 | 204 | Create frontend for notification acknowledgment | Notification and Reminder Workflow | [6 empty] | UI for marking notifications as "read" or "completed" | Includes filters for read/unread and acknowledged notifications.
105 | 205 | Test trigger event detection workflows | Notification and Reminder Workflow | [6 empty] | Fully tested workflows for detecting and initiating notifications | Verify proper trigger detection for all specified events.
106 | 206 | Test notification delivery across channels | Notification and Reminder Workflow | [6 empty] | Fully tested notification delivery system for email, in-app, and push channels | Ensure accurate delivery and formatting of notifications.
107 | 207 | Test notification acknowledgment functionality | Notification and Reminder Workflow | [6 empty] | Fully tested workflows for marking notifications as acknowledged | Verify notifications are properly marked as "read" or "completed."
108 | 208 | Performance testing for notification system | Notification and Reminder Workflow | [6 empty] | Performance-tested notification system under high load | Ensure scalability for high volumes of notifications and concurrent acknowledgments.
109 | 209 | Develop backend API for managing "My Template" section | My Template Workflow | [6 empty] | API for retrieving, creating, modifying, deleting, and archiving templates | Organizes templates by categories (e.g., Risk Assessment, Property Survey, Fire Safety Audit).
110 | 210 | Create frontend for accessing "My Template" section | My Template Workflow | [6 empty] | UI for displaying user-created templates organized by categories | Includes filters for categories and search functionality.
111 | 211 | Implement functionality for creating new templates | My Template Workflow | [6 empty] | Logic to save new templates with details and fields to the database | Fields: Name, Category, Description, Custom Fields (text inputs, dropdowns, pictures, etc.).
112 | 212 | Create frontend for template creation | My Template Workflow | [6 empty] | UI for adding new templates with customizable fields | Includes form with preview mode and unique identifier assignment.
113 | 213 | Implement functionality to modify existing templates | My Template Workflow | [6 empty] | Logic to edit and save changes to templates | Supports saving as a new version or overwriting the existing version.
114 | 214 | Create frontend for modifying templates | My Template Workflow | [6 empty] | UI for editing template fields, layout, or configurations | Includes options for version control.
115 | 215 | Implement delete and archive functionality for templates | My Template Workflow | [6 empty] | Logic for deleting or archiving templates | Archived templates are non-editable but accessible for reference.
116 | 216 | Create frontend for delete and archive actions | My Template Workflow | [6 empty] | UI for managing template status (active, archived, or deleted) | Includes confirmation modals for deletion or archival actions.
117 | 217 | Test template creation and organization workflows | My Template Workflow | [6 empty] | Fully tested workflows for creating and categorizing templates | Verify templates are saved correctly and categorized properly.
118 | 218 | Test template modification and version control | My Template Workflow | [6 empty] | Fully tested workflows for modifying templates | Ensure changes are saved as new versions or overwrite the existing template.
119 | 219 | Test delete and archive functionalities | My Template Workflow | [6 empty] | Fully tested workflows for deleting or archiving templates | Verify archived templates are non-editable but viewable; deleted templates are removed.
120 | 220 | Performance testing for "My Template" module | My Template Workflow | [6 empty] | Performance-tested "My Template" section under high user load | Ensure smooth operation with a large number of templates and users accessing the module.
121 | 221 | Develop backend API for managing Template Center | Template Center Workflow | [6 empty] | API for retrieving and managing pre-created templates by Admin/Company | Templates include descriptions, categories, and usage instructions.
122 | 222 | Create frontend for accessing Template Center | Template Center Workflow | [6 empty] | UI for displaying pre-created templates organized by categories | Includes filters and a search bar for easy navigation.
123 | 223 | Implement search and filter functionality | Template Center Workflow | [6 empty] | Backend logic for searching and filtering templates | Filters: Category, Keywords, Date Added, Popularity.
124 | 224 | Create frontend for search and filter templates | Template Center Workflow | [6 empty] | UI for applying search and filters in the Template Center | Includes dynamic filtering and instant search results display.
125 | 225 | Implement save functionality for "Save to My Template" | Template Center Workflow | [6 empty] | Logic to copy selected templates from Template Center to My Template | Ensures proper linking and versioning of saved templates.
126 | 226 | Create frontend for saving templates to My Template | Template Center Workflow | [6 empty] | Button and confirmation for saving templates to My Template | Includes success message and navigation to My Template section.
127 | 227 | Implement template modification functionality | Template Center Workflow | [6 empty] | Logic to allow modifications of saved templates in My Template | Supports full customization of template fields and layout.
128 | 228 | Create frontend for modifying saved templates | Template Center Workflow | [6 empty] | UI for editing saved templates | Includes options for renaming, field changes, and layout updates.
129 | 229 | Test Template Center access and organization workflows | Template Center Workflow | [6 empty] | Fully tested workflows for accessing and categorizing templates | Verify templates are properly categorized and displayed accurately.
130 | 230 | Test search and filter functionalities | Template Center Workflow | [6 empty] | Fully tested workflows for searching and filtering templates | Verify search accuracy and dynamic filtering performance.
131 | 231 | Test "Save to My Template" workflows | Template Center Workflow | [6 empty] | Fully tested workflows for saving templates to My Template | Ensure saved templates appear in My Template and are ready for customization.
132 | 232 | Test template modification workflows | Template Center Workflow | [6 empty] | Fully tested workflows for modifying saved templates | Ensure changes to saved templates are applied and saved correctly.
133 | 233 | Performance testing for Template Center | Template Center Workflow | [6 empty] | Performance-tested Template Center under high user load | Ensure smooth operation with a large number of templates and concurrent users.
134 | 234 | Develop backend API for managing templates in Template Center | Admin Workflow for Template Management | [6 empty] | API for adding, editing, archiving, and deleting templates | Supports fields: Name, Category, Description, Fields, and Guidelines.
135 | 235 | Create frontend for Template Center Management | Admin Workflow for Template Management | [6 empty] | Admin interface for managing templates | Includes sections for adding, editing, and archiving templates.
136 | 236 | Implement template creation functionality | Admin Workflow for Template Management | [6 empty] | Logic for creating and saving new templates | Supports publishing templates directly to Template Center.
137 | 237 | Create frontend for adding new templates | Admin Workflow for Template Management | [6 empty] | UI for creating new templates with detailed input fields | Includes a preview option and validation for required fields.
138 | 238 | Implement template editing functionality | Admin Workflow for Template Management | [6 empty] | Logic to update existing templates | Automatically notifies users when a template is updated.
139 | 239 | Create frontend for editing templates | Admin Workflow for Template Management | [6 empty] | UI for modifying existing templates | Includes version control and change logs for updated templates.
140 | 240 | Implement template archiving functionality | Admin Workflow for Template Management | [6 empty] | Logic to archive templates | Archived templates are removed from active use but retained for historical reference.
141 | 241 | Create frontend for archiving templates | Admin Workflow for Template Management | [6 empty] | UI for archiving templates and managing archived templates | Includes filter options to view active or archived templates.
142 | 242 | Implement template deletion functionality | Admin Workflow for Template Management | [6 empty] | Logic to delete templates permanently | Includes a confirmation mechanism to avoid accidental deletions.
143 | 243 | Create frontend for deleting templates | Admin Workflow for Template Management | [6 empty] | UI for permanently deleting templates | Includes confirmation modals with warnings about irreversible actions.
144 | 244 | Test template creation and publishing workflows | Admin Workflow for Template Management | [6 empty] | Fully tested workflows for creating and publishing templates | Verify templates are published correctly and available in Template Center.
145 | 245 | Test template editing workflows | Admin Workflow for Template Management | [6 empty] | Fully tested workflows for modifying and updating templates | Ensure updated templates reflect changes across the system.
146 | 246 | Test template archiving and deletion workflows | Admin Workflow for Template Management | [6 empty] | Fully tested workflows for archiving and deleting templates | Verify archived templates remain accessible for reference; deleted templates are removed.
147 | 247 | Performance testing for Template Center Management | Admin Workflow for Template Management | [6 empty] | Performance-tested admin module for managing templates | Ensure smooth operation with a large number of templates and admin actions.

## BE - Additional Tasks
SN | Task ID | Task | Module | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
1 | 248 | Define roles and permissions for template management | Company Management Workflow | [6 empty] | Role-based access controls for template actions | Roles: Super Admin, Manager. Permissions for add, edit, archive, and delete.
2 | 249 | Create and manage template categories | Company Management Workflow | [6 empty] | Logic for adding and managing categories for templates | Supports better organization and filtering.
3 | 250 | Create frontend for category management | Company Management Workflow | [6 empty] | UI for admins to create and manage template categories | Includes dropdowns for assigning templates to categories.
4 | 251 | Implement template versioning system | Company Management Workflow | [6 empty] | Logic to automatically generate and track template versions | Supports viewing version history and reverting to previous versions.
5 | 252 | Create frontend for version control | Company Management Workflow | [6 empty] | UI to view version history and revert templates | Includes visual comparison of versions.
6 | 253 | Enable bulk actions for templates | Company Management Workflow | [6 empty] | Logic for bulk archiving or deleting templates | Includes confirmation prompts to prevent accidental changes.
7 | 254 | Create frontend for bulk actions | Company Management Workflow | [6 empty] | UI for selecting multiple templates for bulk actions | Includes select all, deselect all, and action buttons.
8 | 255 | Notify users of template updates | Company Management Workflow | [6 empty] | Notification system for template additions, edits, and archives | Includes in-app and email notification options.
9 | 256 | Create frontend for notification settings | Company Management Workflow | [6 empty] | UI to configure notification preferences for template updates | Users can opt in or out of specific notifications.
10 | 257 | Implement audit logs for template management | Company Management Workflow | [6 empty] | Logs for all admin actions related to templates | Includes logs for creation, edits, archives, and deletions.
11 | 258 | Create frontend for viewing audit logs | Company Management Workflow | [6 empty] | UI for admins to view and filter audit logs | Includes filters for date, user, and action type.
12 | 259 | Implement export/import functionality for templates | Company Management Workflow | [6 empty] | Logic to export templates to CSV/JSON and import into Template Center | Supports offline editing and bulk uploads.
13 | 260 | Create frontend for export/import templates | Company Management Workflow | [6 empty] | UI for admins to export or import templates | Includes file validation and error handling for imports.
14 | 261 | Validate template name uniqueness | Company Management Workflow | [6 empty] | Logic to prevent duplicate template names | Includes error messages for duplicate submissions.
15 | 262 | Implement approval workflow for publishing templates | Company Management Workflow | [6 empty] | Logic for draft and approval stages for templates | Templates remain in draft until reviewed and approved by designated admins.
16 | 263 | Create frontend for template approval workflow | Company Management Workflow | [6 empty] | UI for reviewing and approving draft templates | Includes status indicators for drafts and approvals.
17 | 264 | Implement bulk actions for client profiles | Client Management Workflow | [6 empty] | Logic for bulk adding, updating, and deleting clients | Includes confirmation prompts and logs for all bulk actions.
18 | 265 | Create frontend for bulk client actions | Client Management Workflow | [6 empty] | UI for selecting and performing bulk actions on clients | Features include select all, deselect all, and bulk action dropdown.
19 | 266 | Implement advanced search and filters for clients | Client Management Workflow | [6 empty] | Logic for advanced filtering and search by industry, location, and activity | Includes an option to save frequently used search criteria.
20 | 267 | Create frontend for advanced search and filters | Client Management Workflow | [6 empty] | UI for applying advanced search and filter options | Dynamic filtering and instant search results display.
21 | 268 | Add client segmentation logic | Client Management Workflow | [6 empty] | Functionality to group clients based on attributes | Supports reporting and targeted communication.
22 | 269 | Enable notes and attachments for client profiles | Client Management Workflow | [6 empty] | Logic to add and manage notes and attachments for clients | Includes file uploads and secure storage.
23 | 270 | Create frontend for notes and attachments | Client Management Workflow | [6 empty] | UI for adding and viewing notes and attachments | Features include a timeline view of interactions.
24 | 271 | Implement client lifecycle stages | Client Management Workflow | [6 empty] | Logic for tracking client lifecycle stages (e.g., prospect, active, inactive) | Supports automated workflows for transitioning stages.
25 | 272 | Create frontend for managing client lifecycle stages | Client Management Workflow | [6 empty] | UI for updating and viewing client lifecycle stages | Includes visual indicators for lifecycle stages.
26 | 273 | Enable integration with external CRM systems | Client Management Workflow | [6 empty] | Logic for syncing client data with external CRMs like Salesforce or HubSpot | Supports bidirectional data synchronization.
27 | 274 | Create import/export functionality for clients | Client Management Workflow | [6 empty] | Logic to import/export client data in CSV/JSON format | Ensures compatibility with external systems and manual data handling.
28 | 275 | Validate client details in real-time | Client Management Workflow | [6 empty] | Logic for real-time validation of client details | Checks include email format, duplicate entries, and required fields.
29 | 276 | Create frontend for validation feedback | Client Management Workflow | [6 empty] | UI for displaying validation errors and suggestions | Includes meaningful error messages and input correction hints.
30 | 277 | Implement granular user roles and permissions | Client Management Workflow | [6 empty] | Access controls for viewing, editing, and deleting client profiles | Roles: Admin, Manager, Viewer. Permissions depend on user role.
31 | 278 | Test lifecycle stages and segmentation features | Client Management Workflow | [6 empty] | Fully tested client lifecycle and segmentation functionalities | Verify proper transitions between lifecycle stages and accurate segmentation.
32 | 279 | Test bulk client actions and validation workflows | Client Management Workflow | [6 empty] | Fully tested bulk client management and validation features | Ensure bulk updates and validations work without data loss or duplication.
33 | 280 | Implement recurring event scheduling | Calendar Scheduling Workflow | [6 empty] | Logic to enable scheduling recurring events with custom patterns | Options for daily, weekly, monthly recurrence and end dates.
34 | 281 | Create frontend for recurring events | Calendar Scheduling Workflow | [6 empty] | UI for configuring recurring tasks in the calendar | Includes visual indicators for recurring tasks.
35 | 282 | Enable event dependencies | Calendar Scheduling Workflow | [6 empty] | Logic for linking events with dependencies | Dependencies like "Task B starts after Task A is completed."
36 | 283 | Create frontend for event dependencies | Calendar Scheduling Workflow | [6 empty] | UI to visually represent dependencies between events | Includes arrows or links between dependent events on the calendar.
37 | 284 | Add time zone management for calendar events | Calendar Scheduling Workflow | [6 empty] | Display and adjust events based on user’s local time zone | Supports company-wide default time zones and user-specific overrides.
38 | 285 | Create frontend for time zone settings | Calendar Scheduling Workflow | [6 empty] | UI to configure and view calendar events in different time zones | Includes a toggle for displaying in local or default time zones.
39 | 286 | Enable drag-and-drop rescheduling functionality | Calendar Scheduling Workflow | [6 empty] | Drag-and-drop interface for rescheduling events | Includes conflict detection for overlapping tasks.
40 | 287 | Implement event conflict detection | Calendar Scheduling Workflow | [6 empty] | Logic to detect and notify users of scheduling conflicts | Suggestions for resolving conflicts (e.g., alternative times).
41 | 288 | Create bulk event management functionality | Calendar Scheduling Workflow | [6 empty] | Logic for bulk updating or deleting calendar events | Includes confirmation prompts for bulk actions.
42 | 289 | Add advanced filters and search for events | Calendar Scheduling Workflow | [6 empty] | Advanced filtering options for events by status, personnel, or priority | Includes search bar for quick event location.
43 | 290 | Create frontend for advanced filters and search | Calendar Scheduling Workflow | [6 empty] | UI to apply filters and perform advanced searches on the calendar | Includes dynamic filtering and live search results display.
44 | 291 | Enable offline access for calendar events | Calendar Scheduling Workflow | [6 empty] | Offline mode for mobile users to view and update calendar events | Sync changes automatically when online.
45 | 292 | Implement event analytics module | Calendar Scheduling Workflow | [6 empty] | Generate analytics on calendar usage and event trends | Includes most scheduled tasks, busiest personnel, and busiest time slots.
46 | 293 | Create frontend for event analytics | Calendar Scheduling Workflow | [6 empty] | UI for viewing calendar analytics | Includes charts and graphs for insights.
47 | 294 | Add customizable notifications for events | Calendar Scheduling Workflow | [6 empty] | Notification system with user-defined preferences | Options for email, push notifications, and in-app alerts.
48 | 295 | Create frontend for customizable notifications | Calendar Scheduling Workflow | [6 empty] | UI to configure notification preferences | Includes toggles for notification types and timing.
49 | 296 | Implement multiple calendar views | Calendar Scheduling Workflow | [6 empty] | Options for daily, weekly, monthly, and list views | Users can toggle between views based on preference.
50 | 297 | Enable calendar sharing functionality | Calendar Scheduling Workflow | [6 empty] | Logic for sharing calendars with other users or teams | Includes view-only or edit access options.
51 | 298 | Create frontend for shared calendars | Calendar Scheduling Workflow | [6 empty] | UI for managing shared calendar access | Includes options to set permissions for shared users.
52 | 299 | Implement template sharing functionality | Assessment Templates Creation Workflow | [6 empty] | Logic to allow sharing templates with teams or departments | Includes view-only and edit access options.
53 | 300 | Create frontend for sharing templates | Assessment Templates Creation Workflow | [6 empty] | UI for sharing templates with specific users or groups | Includes notification for shared templates.
54 | 301 | Add analytics for template usage | Assessment Templates Creation Workflow | [6 empty] | Logic to track and display template usage metrics | Includes insights like most frequently used templates or fields.
55 | 302 | Create frontend for template analytics | Assessment Templates Creation Workflow | [6 empty] | UI to display usage statistics and insights for templates | Includes charts and graphs for visualization.
56 | 303 | Enable collaborative editing for templates | Assessment Templates Creation Workflow | [6 empty] | Logic to support real-time collaborative editing | Includes activity logs to track user contributions.
57 | 304 | Create frontend for collaborative editing | Assessment Templates Creation Workflow | [6 empty] | UI to allow multiple users to edit a template simultaneously | Includes visual indicators for active collaborators.
58 | 305 | Implement template cloning functionality | Assessment Templates Creation Workflow | [6 empty] | Logic to duplicate templates for modification without affecting the original | Supports custom naming for cloned templates.
59 | 306 | Create frontend for cloning templates | Assessment Templates Creation Workflow | [6 empty] | UI to clone templates and display duplicates in "My Templates" | Includes confirmation for cloning.
60 | 307 | Add advanced field customization for templates | Assessment Templates Creation Workflow | [6 empty] | Logic for adding conditional fields and drag-and-drop arrangement | Supports dynamic field visibility based on prior answers.
61 | 308 | Create frontend for advanced field customization | Assessment Templates Creation Workflow | [6 empty] | UI for configuring conditional fields and rearranging them | Includes live preview of changes.
62 | 309 | Implement export/import functionality for templates | Assessment Templates Creation Workflow | [6 empty] | Logic to export templates to JSON/XML and import them into the system | Supports compatibility with external tools.
63 | 310 | Create frontend for export/import templates | Assessment Templates Creation Workflow | [6 empty] | UI for exporting and importing templates | Includes file validation and error handling for imports.
64 | 311 | Implement multi-language support for templates | Assessment Templates Creation Workflow | [6 empty] | Logic to translate templates into multiple languages | Allows switching between languages in the template interface.
65 | 312 | Create frontend for multi-language templates | Assessment Templates Creation Workflow | [6 empty] | UI for selecting and viewing templates in different languages | Includes default language configuration.
66 | 313 | Add dynamic pre-filled fields to templates | Assessment Templates Creation Workflow | [6 empty] | Logic to auto-populate fields based on user input or external integrations | Reduces manual input for repetitive data.
67 | 314 | Enable template approval workflow | Assessment Templates Creation Workflow | [6 empty] | Logic to allow admins to review and approve templates before publishing | Includes draft and published status for templates.
68 | 315 | Create frontend for template approval workflow | Assessment Templates Creation Workflow | [6 empty] | UI for reviewing and approving templates | Includes status indicators for drafts and approvals.
69 | 316 | Implement template archival rules | Assessment Templates Creation Workflow | [6 empty] | Logic to automatically archive templates based on age or inactivity | Sends notifications before archival.
70 | 317 | Create frontend for managing template archival rules | Assessment Templates Creation Workflow | [6 empty] | UI for setting archival criteria and viewing archived templates | Includes filters for active and archived templates.
71 | 318 | Test collaborative editing functionality | Assessment Templates Creation Workflow | [6 empty] | Fully tested collaborative template editing workflows | Ensure real-time updates and accurate change tracking.
72 | 319 | Test template approval workflow | Assessment Templates Creation Workflow | [6 empty] | Fully tested approval process for publishing templates | Verify notification triggers and status updates.
73 | 320 | Implement dynamic content generation for reports | Generate Report Workflow | [6 empty] | Logic to include conditional sections based on user input or assessment data | Supports conditional content like compliance-specific sections.
74 | 321 | Enable creation of custom report templates | Generate Report Workflow | [6 empty] | Logic to save predefined layouts, sections, and branding for reports | Includes user-defined templates for repeated use.
75 | 322 | Create frontend for custom report templates | Generate Report Workflow | [6 empty] | UI to create and save custom templates | Includes options for adding sections, branding, and layouts.
76 | 323 | Add branding customization options for reports | Generate Report Workflow | [6 empty] | Logic to incorporate company logos, headers, footers, and color schemes | Enhances report personalization for professional use.
77 | 324 | Create frontend for branding customization | Generate Report Workflow | [6 empty] | UI for uploading logos and customizing colors/fonts | Includes live preview of branding changes.
78 | 325 | Implement data validation for report generation | Generate Report Workflow | [6 empty] | Logic to validate assessment data before generating reports | Provides warnings for missing or incomplete fields.
79 | 326 | Enable collaboration on report generation | Generate Report Workflow | [6 empty] | Real-time collaboration logic with activity logs | Tracks user changes and supports locking to prevent overwrites.
80 | 327 | Create frontend for collaborative report editing | Generate Report Workflow | [6 empty] | UI for collaborative editing and viewing activity logs | Includes visual indicators for active collaborators.
81 | 328 | Develop scheduled report generation system | Generate Report Workflow | [6 empty] | Logic for scheduling automatic report generation at predefined intervals | Supports notifications for scheduled report completion.
82 | 329 | Add multi-language support for reports | Generate Report Workflow | [6 empty] | Logic to generate reports in multiple languages | Allows language selection during report generation.
83 | 330 | Create frontend for multi-language report options | Generate Report Workflow | [6 empty] | UI to select and view reports in different languages | Includes a default language configuration option.
84 | 331 | Integrate report generation with external tools | Generate Report Workflow | [6 empty] | Logic to export reports to formats like CSV, JSON, Excel | Includes integration with analytics platforms like Power BI or Excel.
85 | 332 | Add audit logs for report actions | Generate Report Workflow | [6 empty] | Logs for tracking report generation, modification, and sharing | Ensures compliance and accountability for report actions.
86 | 333 | Create frontend for audit logs related to reports | Generate Report Workflow | [6 empty] | UI to display audit logs for report-related actions | Includes filters for date, user, and type of action.
87 | 334 | Implement AI-powered insights in reports | Generate Report Workflow | [6 empty] | Logic to highlight key risks, trends, or anomalies in reports | Users can toggle AI-generated summaries.
88 | 335 | Add version control for reports | Generate Report Workflow | [6 empty] | Logic to maintain report version history | Allows users to revert to previous versions if needed.
89 | 336 | Create frontend for report version control | Generate Report Workflow | [6 empty] | UI to view, compare, and revert to previous report versions | Includes visual indicators for version differences.
90 | 337 | Enable report comparison functionality | Generate Report Workflow | [6 empty] | Logic to compare two or more reports side-by-side | Identifies trends or discrepancies between reports.
91 | 338 | Create frontend for report comparison | Generate Report Workflow | [6 empty] | UI to display side-by-side comparison of reports | Includes visual highlights for differences in sections or data.
92 | 339 | Implement Two-Factor Authentication (2FA) | User Management Workflow | [6 empty] | Logic to enable 2FA during user setup or login | Supports email-based and app-based authentication.
93 | 340 | Create frontend for 2FA setup | User Management Workflow | [6 empty] | UI for enabling and configuring 2FA | Includes setup guidance for users.
94 | 341 | Add functionality for user groups | User Management Workflow | [6 empty] | Logic to group users into teams or departments | Supports group-level permissions and management.
95 | 342 | Create frontend for managing user groups | User Management Workflow | [6 empty] | UI for creating and managing user groups | Includes group permissions overview and editing options.
96 | 343 | Develop user activity dashboard | User Management Workflow | [6 empty] | Logic to generate user activity statistics | Includes login trends, most active users, and usage data.
97 | 344 | Create frontend for user activity dashboard | User Management Workflow | [6 empty] | UI for displaying user activity and system usage metrics | Includes filters for date range and user roles.
98 | 345 | Enable custom user roles creation | User Management Workflow | [6 empty] | Logic to define and manage custom roles | Supports role-specific permissions and modification options.
99 | 346 | Create frontend for custom roles management | User Management Workflow | [6 empty] | UI for creating, editing, and deleting custom roles | Includes role assignment for specific users or groups.
100 | 347 | Add bulk user actions functionality | User Management Workflow | [6 empty] | Logic for bulk adding, updating, or deactivating multiple users | Includes confirmation prompts and audit logs for bulk changes.
101 | 348 | Create frontend for bulk user actions | User Management Workflow | [6 empty] | UI for performing bulk actions on users | Includes select all, deselect all, and action dropdown.
102 | 349 | Add functionality for user suspension/reactivation | User Management Workflow | [6 empty] | Logic to temporarily suspend and reactivate user accounts | Retains account activity logs for reactivated users.
103 | 350 | Enable advanced filters and search for users | User Management Workflow | [6 empty] | Advanced filtering and search options based on roles, activity status, etc. | Supports global user lookup via a search bar.
104 | 351 | Create frontend for advanced user search | User Management Workflow | [6 empty] | UI for filtering and searching users | Includes dynamic filtering and instant search results.
105 | 352 | Implement configurable password policies | User Management Workflow | [6 empty] | Logic to enforce password strength and expiration policies | Includes automated reminders for password expiry.
106 | 353 | Create frontend for password policy settings | User Management Workflow | [6 empty] | UI for admins to configure password policies | Includes real-time password strength validation.
107 | 354 | Add user notification preferences management | User Management Workflow | [6 empty] | Logic for user-defined notification settings | Allows customization for email, push, and in-app notifications.
108 | 355 | Create frontend for notification preferences | User Management Workflow | [6 empty] | UI to configure and view notification preferences | Includes toggles for notification types and delivery channels.
109 | 356 | Develop onboarding guide for new users | User Management Workflow | [6 empty] | UI for step-by-step onboarding for new users | Includes interactive tutorials and feature highlights.
110 | 357 | Implement audit logs for user permission changes | User Management Workflow | [6 empty] | Logs for tracking who made changes to user permissions | Provides transparency and accountability for admin actions.
111 | 358 | Create frontend for viewing audit logs | User Management Workflow | [6 empty] | UI to display logs for permission changes | Includes filters for date, user, and type of change.
112 | 359 | Enable session management for active users | User Management Workflow | [6 empty] | Logic to view and terminate active sessions | Includes session timeout for idle users.
113 | 360 | Create frontend for session management | User Management Workflow | [6 empty] | UI for viewing and terminating active sessions | Includes warnings for users about impending session terminations.
114 | 361 | Add data privacy settings for users | User Management Workflow | [6 empty] | Logic to allow users to manage data privacy settings | Includes options for data download and deletion for GDPR compliance.
115 | 362 | Enable login attempt monitoring | User Management Workflow | [6 empty] | Logic to track failed login attempts and notify users of suspicious activity | Includes account lockout for repeated failed attempts.
116 | 363 | Add integration with external HR tools | User Management Workflow | [6 empty] | Logic to sync user details with external systems like BambooHR | Includes APIs for external tool integration.
117 | 364 | Generate user activity reports | User Management Workflow | [6 empty] | Logic to create reports on user activity, login trends, and role distribution | Supports export in formats like CSV or PDF.
118 | 365 | Add functionality for creating customizable plans | Subscription Workflow | [6 empty] | Logic for admins to create and manage subscription plans | Includes one-time, recurring, and tiered pricing structures.
119 | 366 | Enable discounts and coupons for subscriptions | Subscription Workflow | [6 empty] | Logic for generating and validating discount codes | Includes integration with the payment gateway for applying discounts.
120 | 367 | Create frontend for managing discounts and coupons | Subscription Workflow | [6 empty] | UI for admins to add and manage discount codes | Includes fields for discount percentage, duration, and validation criteria.
121 | 368 | Add support for free trials | Subscription Workflow | [6 empty] | Logic for managing free trial subscriptions | Automatically transitions to paid plans after trial expiration with notifications.
122 | 369 | Integrate multiple payment gateways | Subscription Workflow | [6 empty] | Logic for supporting PayPal, Razorpay, and other payment gateways | Allows users to select their preferred payment methods.
123 | 370 | Implement tax calculation based on location | Subscription Workflow | [6 empty] | Logic to calculate and apply regional taxes (e.g., VAT, GST) | Generates tax-compliant invoices and receipts.
124 | 371 | Enable subscription pause and resume functionality | Subscription Workflow | [6 empty] | Logic for temporarily pausing and resuming subscriptions | Sends notifications about access and billing changes during pauses.
125 | 372 | Add advanced renewal settings | Subscription Workflow | [6 empty] | Logic for flexible renewal options like auto-renew and manual renewals | Includes reminders for upcoming renewals.
126 | 373 | Implement usage-based billing | Subscription Workflow | [6 empty] | Logic to calculate charges based on actual usage | Displays usage metrics in the subscription dashboard.
127 | 374 | Develop admin insights for subscriptions | Subscription Workflow | [6 empty] | Analytics dashboard with trends, churn rates, and revenue breakdown | Supports export of subscription-related data for reports.
128 | 375 | Add multi-currency support for payments | Subscription Workflow | [6 empty] | Logic for processing payments in multiple currencies | Displays available currency options during plan selection and billing.
129 | 376 | Create plan comparison tool | Subscription Workflow | [6 empty] | UI for comparing subscription plans side-by-side | Highlights differences in features and pricing.
130 | 377 | Enable subscription upgrade recommendations | Subscription Workflow | [6 empty] | Logic to recommend plan upgrades based on usage patterns | Includes notifications for users nearing plan limits.
131 | 378 | Implement centralized notification center | Subscription Workflow | [6 empty] | Logic to aggregate subscription-related updates in one place | Includes reminders, upgrades, and billing notifications.
132 | 379 | Create mobile-friendly subscription management UI | Subscription Workflow | [6 empty] | Mobile-optimized interface for billing, upgrades, and renewals | Ensures seamless subscription access on mobile devices.
133 | 380 | Implement role-based access for subscription features | Subscription Workflow | [6 empty] | Logic to restrict subscription management to specific roles | Includes access logs for subscription-related actions.
134 | 381 | Add fraud prevention mechanisms | Subscription Workflow | [6 empty] | Logic to detect and prevent fraudulent subscription transactions | Includes CAPTCHA or verifications for high-value transactions.
135 | 382 | Develop API for third-party subscription integration | Subscription Workflow | [6 empty] | API for syncing subscription data with external tools like CRMs | Supports integration with platforms like Salesforce or accounting tools.
136 | 383 | Enable custom invoices with branding | Subscription Workflow | [6 empty] | Logic to generate detailed, branded invoices | Includes itemized billing and tax breakdowns.
137 | 384 | Add churn management tools | Subscription Workflow | [6 empty] | Logic to identify and retain users at risk of canceling subscriptions | Includes automated retention campaigns like discounts or personalized offers.
138 | 385 | Implement AI-powered revenue forecasting | Subscription Workflow | [6 empty] | Logic to predict revenue trends based on subscription data | Highlights growth opportunities or risks for admin insights.
139 | 386 | Implement priority levels for notifications | Notification and Reminder Workflow | [6 empty] | Logic to assign and display priority levels for notifications | High-priority notifications displayed more prominently.
140 | 387 | Enable recurring notifications | Notification and Reminder Workflow | [6 empty] | Logic to set up notifications for recurring tasks or events | Users can configure frequency (e.g., daily, weekly, monthly).
141 | 388 | Create custom notification templates | Notification and Reminder Workflow | [6 empty] | Logic to manage pre-defined and customizable templates for notifications | Supports dynamic placeholders (e.g., {UserName}, {TaskName}).
142 | 389 | Add multi-channel notification support | Notification and Reminder Workflow | [6 empty] | Logic for sending notifications via SMS, in addition to email, in-app, and push | Includes channel configuration for users.
143 | 390 | Implement read receipt tracking | Notification and Reminder Workflow | [6 empty] | Logic to track and display notification read status | Provides insights for admin on engagement levels.
144 | 391 | Enable actionable notifications | Notification and Reminder Workflow | [6 empty] | Logic for embedding action buttons in notifications | Examples: "Approve," "Complete Task."
145 | 392 | Add functionality for group notifications | Notification and Reminder Workflow | [6 empty] | Logic to send notifications to specific user groups | Includes group acknowledgment tracking.
146 | 393 | Implement notification scheduling | Notification and Reminder Workflow | [6 empty] | Logic for scheduling notifications for specific times | Supports time zone adjustments for scheduling.
147 | 394 | Enable personalized notifications | Notification and Reminder Workflow | [6 empty] | Logic to tailor notifications based on user preferences or activity patterns | Includes AI-based personalization suggestions.
148 | 395 | Develop centralized notification center | Notification and Reminder Workflow | [6 empty] | UI for users to view, filter, and manage all notifications | Includes filters for type, priority, and status.
149 | 396 | Add notification snooze functionality | Notification and Reminder Workflow | [6 empty] | Logic to allow users to snooze notifications for a defined period | Sends reminders for snoozed notifications.
150 | 397 | Implement notification history | Notification and Reminder Workflow | [6 empty] | Logic to store and display past notifications for users | Includes search functionality for past notifications.
151 | 398 | Optimize notifications for mobile devices | Notification and Reminder Workflow | [6 empty] | Mobile-optimized UI for managing and receiving notifications | Supports swipe actions for acknowledgment or dismissal.
152 | 399 | Enable custom notification sounds | Notification and Reminder Workflow | [6 empty] | Logic to allow users to set custom sounds for notifications | Includes mute options for specific notification types.
153 | 400 | Provide analytics for notification engagement | Notification and Reminder Workflow | [6 empty] | Admin dashboard to view notification delivery and acknowledgment rates | Includes export options for analytics data.
154 | 401 | Add role-based permissions for notifications | Notification and Reminder Workflow | [6 empty] | Logic to restrict notification creation and management to specific roles | Includes permission logs for admin actions.
155 | 402 | Implement audit logs for notifications | Notification and Reminder Workflow | [6 empty] | Logs for tracking creation, updates, and deletion of notifications | Supports compliance and accountability.
156 | 403 | Add notification throttling | Notification and Reminder Workflow | [6 empty] | Logic to avoid overwhelming users with too many notifications | Admins can configure frequency thresholds.
157 | 404 | Enable real-time notifications | Notification and Reminder Workflow | [6 empty] | Real-time delivery system using WebSocket or similar technologies | Ensures instant notification for critical updates.
158 | 405 | Add multi-language support for notifications | Notification and Reminder Workflow | [6 empty] | Logic to deliver notifications in users' preferred languages | Admin tools for managing multi-language templates.
159 | 406 | Integrate notifications with external tools | Notification and Reminder Workflow | [6 empty] | APIs for sending notifications to external platforms (e.g., Slack, Teams) | Supports third-party integrations.
160 | 407 | Implement AI-powered insights for notifications | Notification and Reminder Workflow | [6 empty] | AI logic to analyze notification effectiveness and suggest improvements | Highlights patterns in unread or ignored notifications.
161 | 408 | Add user behavior-driven notification triggers | Notification and Reminder Workflow | [6 empty] | Logic to send notifications based on user activity patterns | Examples: inactivity reminders, frequent login failure alerts.
162 | 409 | Enable shared access and collaboration for templates | My Template Workflow | [6 empty] | Logic to allow team members to collaborate on templates | Includes role-based permissions (e.g., View, Edit).
163 | 410 | Create frontend for template collaboration | My Template Workflow | [6 empty] | UI for sharing templates and managing collaborator roles | Includes notifications for collaboration invites.
164 | 411 | Add tagging and metadata for templates | My Template Workflow | [6 empty] | Logic to allow users to add tags or metadata to templates | Tags used for search and filtering in "My Template" section.
165 | 412 | Implement advanced search functionality | My Template Workflow | [6 empty] | Logic to filter templates by tags, creation date, and creator | Includes keyword search across template names and descriptions.
166 | 413 | Add functionality for comparing template versions | My Template Workflow | [6 empty] | Logic to highlight changes between template versions | Supports tracking updates and changes.
167 | 414 | Enable export and import of templates | My Template Workflow | [6 empty] | Logic to export templates as JSON or XML and import from external files | Supports backup and cross-platform sharing.
168 | 415 | Add analytics for template usage | My Template Workflow | [6 empty] | Analytics dashboard for tracking template usage and trends | Includes metrics like most used templates and modifications.
169 | 416 | Allow customizable template categories | My Template Workflow | [6 empty] | Logic for users to create and manage custom categories | Includes drag-and-drop reordering of templates within categories.
170 | 417 | Maintain audit logs for templates | My Template Workflow | [6 empty] | Logs for all actions on templates (e.g., creation, edits, deletions) | Admins can view logs for compliance and accountability.
171 | 418 | Enable template cloning functionality | My Template Workflow | [6 empty] | Logic to duplicate existing templates for creating new ones | Cloned templates can be modified without affecting the original.
172 | 419 | Add preview mode for templates | My Template Workflow | [6 empty] | UI for previewing templates before saving | Shows how the template appears on different devices.
173 | 420 | Enable offline template access and editing | My Template Workflow | [6 empty] | Logic to sync offline edits once users reconnect | Supports uninterrupted editing in low-connectivity areas.
174 | 421 | Add multi-language support for templates | My Template Workflow | [6 empty] | Logic to save templates in multiple languages | Users can switch between languages while viewing or editing.
175 | 422 | Optimize "My Template" section for mobile users | My Template Workflow | [6 empty] | Mobile-friendly interface for accessing, editing, and managing templates | Ensures full functionality on mobile devices.
176 | 423 | Implement template approval workflow | My Template Workflow | [6 empty] | Logic to review and approve templates before publishing | Supports admin-defined review processes.
177 | 424 | Create frontend for template approval workflow | My Template Workflow | [6 empty] | UI for reviewing and approving templates | Includes notifications for pending approvals.
178 | 425 | Enable global templates for admin users | My Template Workflow | [6 empty] | Logic for admins to create templates accessible to all users | Users can save global templates to their "My Template" section for customization.
179 | 426 | Add template expiry settings | My Template Workflow | [6 empty] | Logic to notify users about template expiry or inactivity | Includes archival of expired templates.
180 | 427 | Provide template usage reports | My Template Workflow | [6 empty] | Reports on template usage trends, popular templates, and modification history | Supports export of report data in CSV or PDF format.
181 | 428 | Implement archival rules for inactive templates | My Template Workflow | [6 empty] | Rules for automatically archiving templates based on inactivity | Notifies users before templates are archived.
182 | 429 | Add AI-powered suggestions for template optimization | My Template Workflow | [6 empty] | AI to suggest improvements based on usage patterns or feedback | Highlights redundant fields or suggests missing sections.
183 | 430 | Enable dynamic templates with external data integration | My Template Workflow | [6 empty] | Logic for templates to auto-populate fields using external data sources | Includes placeholders for real-time data integration.
184 | 431 | Add inter-template linking for modular workflows | My Template Workflow | [6 empty] | Logic to reference or link templates dynamically | Supports workflows where templates are combined automatically.
185 | 432 | Add dynamic filtering options | Template Center Workflow | [6 empty] | Logic to include advanced filters like "Recently Used" and "Most Downloaded" | Supports multiple filter combinations for granular search results.
186 | 433 | Enable template ratings and reviews | Template Center Workflow | [6 empty] | Logic to allow users to rate and review templates | Displays average ratings and user feedback for better selection.
187 | 434 | Develop template usage insights dashboard | Template Center Workflow | [6 empty] | Analytics for template downloads, usage trends, and active users | Admins can monitor template performance.
188 | 435 | Implement bulk template management | Template Center Workflow | [6 empty] | Logic for selecting multiple templates for bulk actions | Includes download, saving, and categorization options.
189 | 436 | Add AI-powered personalized template recommendations | Template Center Workflow | [6 empty] | Logic to recommend templates based on user activity and preferences | Highlights new and trending templates for users.
190 | 437 | Implement template approval workflow | Template Center Workflow | [6 empty] | Logic for admins to review and approve templates before publication | Includes status tags like "Pending," "Approved," and "Rejected."
191 | 438 | Enable global and private templates | Template Center Workflow | [6 empty] | Logic to manage template visibility for global or private access | Allows admins to define visibility settings.
192 | 439 | Add template expiry and archival features | Template Center Workflow | [6 empty] | Logic to set expiry dates and archive expired templates | Retains historical access for reference.
193 | 440 | Develop template comparison tool | Template Center Workflow | [6 empty] | Logic for side-by-side comparison of templates | Highlights differences in structure, fields, and content.
194 | 441 | Implement version control for templates | Template Center Workflow | [6 empty] | Logic to manage and restore previous versions of templates | Allows users to compare changes between versions.
195 | 442 | Add interactive preview for templates | Template Center Workflow | [6 empty] | UI for exploring fields and layouts of templates before saving | Supports dynamic features preview.
196 | 443 | Enable multi-language support for templates | Template Center Workflow | [6 empty] | Logic to tag templates with available languages | Allows users to filter templates based on language preferences.
197 | 444 | Optimize Template Center for mobile users | Template Center Workflow | [6 empty] | Mobile-friendly interface for navigation, search, and saving templates | Ensures seamless access on mobile devices.
198 | 445 | Add dark mode compatibility | Template Center Workflow | [6 empty] | Dark mode UI for Template Center | Applies user interface preferences across sessions.
199 | 446 | Enhance notifications for template updates | Template Center Workflow | [6 empty] | Logic to notify users of new template additions, updates, or recommendations | Includes delivery preferences for email or in-app notifications.
200 | 447 | Develop template categorization management tools | Template Center Workflow | [6 empty] | Tools for admins to create, edit, or delete template categories | Includes drag-and-drop functionality for organizing templates.
201 | 448 | Provide template access analytics | Template Center Workflow | [6 empty] | Reports on access frequency, active users, and category trends | Supports exporting analytics data for reporting.
202 | 449 | Maintain audit logs for template actions | Template Center Workflow | [6 empty] | Logs for template uploads, edits, deletions, and approvals | Role-based access for viewing logs ensures compliance.
203 | 450 | Implement role-based permissions for templates | Template Center Workflow | [6 empty] | Logic to restrict editing, uploading, or deleting templates to specific roles | Ensures secure and controlled access to the Template Center.
204 | 451 | Integrate Template Center with external platforms | Template Center Workflow | [6 empty] | APIs for importing/exporting templates from platforms like SharePoint | Supports third-party integration.
205 | 452 | Add AI-powered search and filter refinement | Template Center Workflow | [6 empty] | AI logic to refine search results and suggest filter combinations | Highlights relevant templates based on user behavior.
206 | 453 | Enable dynamic templates with conditional fields | Template Center Workflow | [6 empty] | Logic for templates to auto-populate based on user input or external data | Includes conditional visibility of fields.
207 | 454 | Develop template subscription feature | Template Center Workflow | [6 empty] | Logic for users to subscribe to specific templates or categories | Notifies users of changes or new additions in subscribed templates/categories.
208 | 455 | Implement bulk template actions | Admin Workflow for Template Management | [6 empty] | Logic for archiving, restoring, or deleting multiple templates | Includes a confirmation prompt and progress tracking for bulk actions.
209 | 456 | Add tools for template categorization | Admin Workflow for Template Management | [6 empty] | Logic to create, edit, and manage template categories | Includes drag-and-drop functionality for reordering templates.
210 | 457 | Develop version control system for templates | Admin Workflow for Template Management | [6 empty] | Logic to maintain version history and restore previous versions | Supports comparison of changes between template versions.
211 | 458 | Implement approval workflow for templates | Admin Workflow for Template Management | [6 empty] | Logic for reviewing and approving templates before publishing | Includes status indicators such as "Draft," "Pending Approval," and "Published."
212 | 459 | Add advanced search and filter functionality | Admin Workflow for Template Management | [6 empty] | Logic to filter templates by creation date, last updated, creator, and category | Includes a global search bar for keyword matching across names and descriptions.
213 | 460 | Enable customizable template guidelines | Admin Workflow for Template Management | [6 empty] | Logic to define and update usage guidelines for templates | Guidelines visible in the Template Center for end users.
214 | 461 | Introduce template lifecycle management | Admin Workflow for Template Management | [6 empty] | Logic to manage lifecycle stages like "Active," "Deprecated," and "Archived" | Includes automated rules for transitioning templates between stages.
215 | 462 | Add interactive preview for templates | Admin Workflow for Template Management | [6 empty] | UI to preview templates on different devices before publishing | Ensures proper formatting and usability for templates.
216 | 463 | Maintain audit logs for template actions | Admin Workflow for Template Management | [6 empty] | Logs for actions like creation, edits, deletions, and approvals | Admins can view logs for compliance and accountability.
217 | 464 | Enable multi-language support for templates | Admin Workflow for Template Management | [6 empty] | Logic for creating, editing, and publishing templates in multiple languages | Includes a language toggle for localized templates in the Template Center.
218 | 465 | Add role-based access control for templates | Admin Workflow for Template Management | [6 empty] | Logic to restrict template management features based on roles | Roles include Creator, Reviewer, and Publisher.
219 | 466 | Develop analytics dashboard for template performance | Admin Workflow for Template Management | [6 empty] | Metrics like most downloaded templates, usage frequency, and user feedback | Includes export options for analytics data.
220 | 467 | Enable scheduled template updates | Admin Workflow for Template Management | [6 empty] | Logic to schedule template updates and notify users of upcoming changes | Supports planning and communication of template changes.
221 | 468 | Add template duplication feature | Admin Workflow for Template Management | [6 empty] | Logic to duplicate templates for faster creation of similar templates | Includes renaming and modification options for duplicated templates.
222 | 469 | Enable collaboration on templates for admins | Admin Workflow for Template Management | [6 empty] | Logic to track changes and allow multiple admins to collaborate | Includes notifications for collaborator activity.
223 | 470 | Integrate templates with external systems | Admin Workflow for Template Management | [6 empty] | APIs for exporting/importing templates to platforms like SharePoint or Google Drive | Supports integration with external platforms and formats like JSON/XML.
224 | 471 | Add AI-powered template improvement suggestions | Admin Workflow for Template Management | [6 empty] | AI logic to suggest optimizations based on usage data or user feedback | Highlights redundant fields or recommends additional sections.
225 | 472 | Enable dynamic templates with conditional fields | Admin Workflow for Template Management | [6 empty] | Logic to auto-populate template fields based on user input or integrations | Includes conditional visibility for specific fields.
226 | 473 | Add template notification settings | Admin Workflow for Template Management | [6 empty] | Logic to notify users about updates to templates they’ve used or downloaded | Includes customization options for notification preferences.
227 | 474 | Ensure GDPR and compliance features for templates | Admin Workflow for Template Management | [6 empty] | Tools to anonymize or delete sensitive data within templates | Ensures compliance with industry or regional regulations.
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245

## Sheet2
Task | Priority | Owner | Status | Start date | End date | Milestone | Deliverable | Notes
| P0 |  | Not started
| P1 |  | In progress
| P2 |  | Blocked
| P3 |  | Completed